## Implementation Roadmap
Phase | Task | Status | Notes
Infrastructure | AWS EC2 Ubuntu Setup | Done | Ubuntu server created
Infrastructure | OpenSSH / SFTP Setup | Done | Password auth enabled for dev
Infrastructure | Create SFTP User | Done | sftpuser
Infrastructure | Create Folders | Done | incoming, processed, failed
Backend | SFTP Connection Service | Pending | ssh2-sftp-client
Backend | List Files API | Pending | GET /api/v1/sftp/test
Backend | Download File | Pending | Download from incoming
Backend | CSV Parser | Pending | Parse CSV
Backend | File Validation | Pending | Filename, header, row count
Backend | Reading Validation | Pending | Business rules
Backend | Save Ingestion Log | Pending | sftp_ingestion_log
Backend | Save Meter Readings | Pending | meter_readings
Backend | Move Files | Pending | processed / failed
Backend | Cron Job | Pending | 00:30 production
Frontend | Dashboard | Pending | Summary cards
Frontend | Files List | Pending | Table
Frontend | File Details | Pending | Drawer
Testing | End-to-End Validation | Pending | Use sample CSV

## APIs
Method | Endpoint | Purpose
GET | /api/v1/sftp/summary | Dashboard summary
GET | /api/v1/sftp/files | Files list
GET | /api/v1/sftp/files/:id | File details
GET | /api/v1/sftp/summary/trend | Trend chart
GET | /api/v1/sftp/missing-files | Missing files
GET | /api/v1/sftp/health | Health
POST | /api/v1/sftp/retrigger | Manual retrigger

## SFTP Structure
Folder | Purpose
incoming | New files uploaded by DTU/client
processed | Successfully processed files
failed | Invalid/failed files